## Project schedule
| CIVE 202 Project #3 |  |  |  |  | Project start: | [7 empty] | 2026-02-26
Jacob Kosmicki
[6 empty] | 2026-02-16 | [6 empty] | 2026-02-23 | [6 empty] | 2026-03-02 | [6 empty] | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23
| TASK | ASSIGNED TO | START | END | time axis 2026-02-16 to 2026-03-29
 | time axis 2026-02-16 to 2026-03-29
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Github Repository
| Create Github | Jacob | 2026-02-26 | 2026-02-26 | 1
| Create README | Jacob | 2026-03-22 | 2026-03-24 | 3
| Upload all Files to Github | Jacob | 2026-03-24 | 2026-03-26 | bar: 2026-02-27
| Review Documents | Jacob | 2026-03-27 | 2026-03-30
| Final Product/Submit | Jacob | 2026-03-31 | 2026-03-31 | 1
Scope of Work
| Identify Clients Tasks | Jacob | 2026-02-26 | 2026-03-02 | 5
| Create SOW | Jacob | 2026-02-27 | 2026-03-10 | 12
| Identify NHTS & NGSIM Variables | Jacob | 2026-03-05 | 2026-03-11 | 7
| Review Document | Jacob | 2026-03-11 | 2026-03-12 | 2
| Final Product/Submit | Jacob | 2026-03-13 | 2026-03-13
Explore NGSIM Dataset
| Bar Chart - NHTS Variable | Jacob | 2026-03-13 | 2026-03-15 | 3
| Histogram - NHTS Variable | Jacob | 2026-03-13 | 2026-03-15 | 3
| Boxplot - NHTS Variable | Jacob | 2026-03-13 | 2026-03-15 | 3
| Time-Series Plot 1 - NGSIM | Jacob | 2026-03-13 | 2026-03-15 | 3
| Time-Series Plot 2 - NGSIM | Jacob | 2026-03-13 | 2026-03-15 | 3
Labs
| Lab #1 | Jacob | 2026-02-27 | 2026-02-27
| Lab #2 | Jacob | 2026-03-06 | 2026-03-06
| Lab #3 | Jacob | 2026-03-13 | 2026-03-13
| Lab #4 | Jacob | 2026-03-27 | 2026-03-27
Python Code
| Review & Revise Plots | Jacob | 2026-03-15 | 2026-03-17 | 3
| IDM Simulation Study | Jacob | 2026-03-16 | 2026-03-18 | 3
| Research Intelligent Driver Model | Jacob | 2026-03-17 | 2026-03-19 | 3
| Code IDM Simulation | Jacob | 2026-03-18 | 2026-03-20 | 3
| Visualize Vehicle Trajectories | Jacob | 2026-03-19 | 2026-03-21 | 3
Annotated Code Document
| Annotate code | Jacob | 2026-03-21 | 2026-03-22 | 2
| Create table of fucntions used' | Jacob | 2026-03-21 | 2026-03-22 | 2
| Review and Submit | Jacob | 2026-03-22 | 2026-03-23 | 2
Written Report
| Draft Introduction & Methods | Jacob | 2026-03-16 | 2026-03-17 | 2
| Draft Results & Discussion | Jacob | 2026-03-17 | 2026-03-27 | 11
| Compile References (APA) | Jacob | 2026-03-27 | 2026-03-28 | 2
| Review & Final Submit | Jacob | 2026-03-31 | 2026-03-31 | 1
| Comments and Dependencies | All submissions are dependent on GitHub. The report is dependent on all the tasks that come before it. For each individual subsection, the tasks beforehand are dependent on the tasks after them. For the document in general, these dependencies are speculations, for the in-depth knowledge of the project is still mainly unknown. For the general document, all dates are speculations, for the only due date actually known is the final submission and labs.

## About
SIMPLE GANTT CHART by Vertex42.com
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.